## 1-RTM
Noel Systems Requirements Traceability Matrix (RTM)
Project Name: Noel Systems Project ID: AII Prepared By: Noel Assegid Date: 2026-12-04] Version: 1.0
Req ID | Requirement Description | Source / Origin | Priority | Design Doc Ref | Dev / Build Ref | Test Case ID | Test Status | Defect ID (if any) | Verification Method | Status | Owner | Comments
REQ-001 | System shall allow users to log in using email and password. | BRD-1.2 | High | DES-LOGIN-01 | US-101 / login.py | TC-001, TC-002 | Passed |  | Test | Verified | J. Smith
REQ-002 | System shall lock account after 5 failed login attempts. | BRD-1.3 | High | DES-LOGIN-02 | US-102 / auth_lock.py | TC-003 | Failed | DEF-014 | Test | In Progress | J. Smith | Retest after fix
REQ-003 | System shall allow password reset via email link. | BRD-1.4 | Medium | DES-LOGIN-03 | US-103 / reset_pw.py | TC-004, TC-005 | Passed |  | Test | Verified | A. Lee
REQ-004 | System shall generate a monthly usage report in PDF format. | SRS-3.1 | Medium | DES-RPT-01 | US-201 / report_gen.py | TC-010 | Not Started |  | Test | Not Started | M. Chen
REQ-005 | System shall comply with WCAG 2.1 AA accessibility standards. | Compliance-1 | High | DES-UI-05 | US-301 / a11y_audit | TC-020, TC-021, TC-022 | In Progress |  | Inspection | In Progress | A. Lee | Third-party audit scheduled
REQ-006 | System shall allow users to update their profile information (name, phone, address). | BRD-2.1 | Medium | DES-PROF-01 | US-104 / profile_edit.py | TC-006 | Passed |  | Test | Verified | A. Lee
REQ-007 | System shall send email notification upon successful profile update. | BRD-2.2 | Low | DES-PROF-02 | US-105 / notify_service.py | TC-007 | Passed |  | Test | Verified | A. Lee
REQ-008 | System shall support two-factor authentication (2FA) via SMS or authenticator app. | SRS-1.5 | High | DES-LOGIN-04 | US-106 / mfa.py | TC-008, TC-009 | In Progress |  | Test | In Progress | J. Smith | Awaiting SMS gateway integration
REQ-009 | System shall log all authentication attempts with timestamp and IP address. | Compliance-2 | High | DES-LOG-01 | US-107 / audit_log.py | TC-011 | Passed |  | Test | Verified | J. Smith
REQ-010 | System shall allow administrators to deactivate user accounts. | BRD-2.5 | Medium | DES-ADMIN-01 | US-108 / admin_deactivate.py | TC-012 | Passed |  | Test | Verified | M. Chen
REQ-011 | System shall allow administrators to reset user passwords on request. | BRD-2.6 | Medium | DES-ADMIN-02 | US-109 / admin_reset_pw.py | TC-013 | Not Started |  | Test | Not Started | M. Chen
REQ-012 | System shall support role-based access control (Admin, Manager, User). | SRS-2.1 | High | DES-RBAC-01 | US-110 / rbac.py | TC-014, TC-015 | In Progress |  | Test | In Progress | J. Smith
REQ-013 | System shall restrict access to admin panel to Admin role only. | SRS-2.2 | High | DES-RBAC-02 | US-111 / rbac_admin.py | TC-016 | Passed |  | Test | Verified | J. Smith
REQ-014 | System shall allow users to upload a profile picture (max 5MB, JPG/PNG). | BRD-2.7 | Low | DES-PROF-03 | US-112 / avatar_upload.py | TC-017 | Passed |  | Test | Verified | A. Lee
REQ-015 | System shall validate uploaded files for malicious content before storage. | Compliance-3 | High | DES-SEC-01 | US-113 / file_scan.py | TC-018 | In Progress |  | Test | In Progress | M. Chen | Pending AV integration
REQ-016 | System shall allow users to search records using keyword search. | SRS-3.2 | Medium | DES-SEARCH-01 | US-202 / search_engine.py | TC-023 | Passed |  | Test | Verified | M. Chen
REQ-017 | System shall support filtering search results by date range and category. | SRS-3.3 | Medium | DES-SEARCH-02 | US-203 / search_filter.py | TC-024, TC-025 | Passed |  | Test | Verified | M. Chen
REQ-018 | System shall paginate search results at 25 items per page. | SRS-3.4 | Low | DES-SEARCH-03 | US-204 / pagination.py | TC-026 | Passed |  | Test | Verified | M. Chen
REQ-019 | System shall export search results to CSV format. | SRS-3.5 | Medium | DES-EXPORT-01 | US-205 / export_csv.py | TC-027 | Not Started |  | Test | Not Started | M. Chen
REQ-020 | System shall generate a weekly summary dashboard for managers. | SRS-3.6 | Medium | DES-RPT-02 | US-206 / dashboard.py | TC-028, TC-029 | In Progress |  | Test | In Progress | M. Chen
REQ-021 | System shall allow scheduling of automated report generation. | SRS-3.7 | Low | DES-RPT-03 | US-207 / report_schedule.py | TC-030 | Not Started |  | Test | Not Started | M. Chen
REQ-022 | System shall support report export in PDF, Excel, and CSV formats. | SRS-3.8 | Medium | DES-RPT-04 | US-208 / report_export.py | TC-031, TC-032, TC-033 | Passed |  | Test | Verified | M. Chen
REQ-023 | System shall retain audit logs for a minimum of 7 years. | Compliance-4 | High | DES-LOG-02 | US-114 / log_retention.py | TC-034 | Passed |  | Inspection | Verified | J. Smith
REQ-024 | System shall encrypt sensitive data at rest using AES-256. | Compliance-5 | High | DES-SEC-02 | US-115 / encryption.py | TC-035 | Passed |  | Analysis | Verified | J. Smith
REQ-025 | System shall encrypt data in transit using TLS 1.2 or higher. | Compliance-6 | High | DES-SEC-03 | US-116 / tls_config.py | TC-036 | Passed |  | Analysis | Verified | J. Smith
REQ-026 | System shall enforce password complexity rules (min 8 chars, mixed case, number, symbol). | SRS-1.6 | High | DES-LOGIN-05 | US-117 / pw_policy.py | TC-037 | Passed |  | Test | Verified | J. Smith
REQ-027 | System shall expire user sessions after 30 minutes of inactivity. | SRS-1.7 | Medium | DES-LOGIN-06 | US-118 / session_timeout.py | TC-038 | Passed |  | Test | Verified | J. Smith
REQ-028 | System shall notify users via email when their password is changed. | SRS-1.8 | Low | DES-LOGIN-07 | US-119 / pw_change_notify.py | TC-039 | Passed |  | Test | Verified | J. Smith
REQ-029 | System shall support single sign-on (SSO) via SAML 2.0. | SRS-1.9 | High | DES-LOGIN-08 | US-120 / saml_sso.py | TC-040, TC-041 | In Progress |  | Test | In Progress | J. Smith | Vendor integration pending
REQ-030 | System shall allow users to view their own activity history. | BRD-2.8 | Low | DES-PROF-04 | US-121 / activity_history.py | TC-042 | Passed |  | Test | Verified | A. Lee
REQ-031 | System shall support multi-language localization (English, Spanish, French). | BRD-3.1 | Medium | DES-I18N-01 | US-122 / localization.py | TC-043, TC-044, TC-045 | In Progress |  | Test | In Progress | A. Lee
REQ-032 | System shall display currency values based on user's regional settings. | BRD-3.2 | Medium | DES-I18N-02 | US-123 / currency_format.py | TC-046 | Not Started |  | Test | Not Started | A. Lee
REQ-033 | System shall support responsive design for mobile, tablet, and desktop. | SRS-4.1 | High | DES-UI-01 | US-302 / responsive_ui.py | TC-047, TC-048, TC-049 | Passed |  | Test | Verified | A. Lee
REQ-034 | System shall load pages within 2 seconds under normal load conditions. | SRS-4.2 | High | DES-PERF-01 | US-303 / perf_optimize.py | TC-050 | In Progress |  | Test | In Progress | M. Chen | Load testing in progress
REQ-035 | System shall support 10,000 concurrent users without degraded performance. | SRS-4.3 | High | DES-PERF-02 | US-304 / load_balancer.py | TC-051 | Not Started |  | Test | Not Started | M. Chen
REQ-036 | System shall provide a REST API for third-party integrations. | SRS-5.1 | Medium | DES-API-01 | US-401 / rest_api.py | TC-052, TC-053 | Passed |  | Test | Verified | J. Smith
REQ-037 | System shall authenticate API requests using OAuth 2.0. | SRS-5.2 | High | DES-API-02 | US-402 / oauth2.py | TC-054 | Passed |  | Test | Verified | J. Smith
REQ-038 | System shall rate-limit API requests to 1000 per hour per client. | SRS-5.3 | Medium | DES-API-03 | US-403 / rate_limit.py | TC-055 | Passed |  | Test | Verified | J. Smith
REQ-039 | System shall provide API documentation via Swagger/OpenAPI. | SRS-5.4 | Low | DES-API-04 | US-404 / api_docs | TC-056 | Passed |  | Inspection | Verified | J. Smith
REQ-040 | System shall support webhook notifications for key events. | SRS-5.5 | Medium | DES-API-05 | US-405 / webhooks.py | TC-057 | Not Started |  | Test | Not Started | J. Smith
REQ-041 | System shall back up database daily with 30-day retention. | SRS-6.1 | High | DES-OPS-01 | US-501 / db_backup.py | TC-058 | Passed |  | Inspection | Verified | M. Chen
REQ-042 | System shall support point-in-time database recovery. | SRS-6.2 | High | DES-OPS-02 | US-502 / db_recovery.py | TC-059 | In Progress |  | Test | In Progress | M. Chen
REQ-043 | System shall provide 99.9% uptime SLA. | SRS-6.3 | High | DES-OPS-03 | US-503 / ha_setup.py | TC-060 | Not Started |  | Analysis | Not Started | M. Chen
REQ-044 | System shall send alerts to operations team when error rate exceeds 5%. | SRS-6.4 | Medium | DES-OPS-04 | US-504 / monitoring.py | TC-061 | Passed |  | Test | Verified | M. Chen
REQ-045 | System shall maintain a status page showing service health. | SRS-6.5 | Low | DES-OPS-05 | US-505 / status_page.py | TC-062 | Passed |  | Inspection | Verified | M. Chen
REQ-046 | System shall allow users to opt out of marketing emails. | Compliance-7 | Medium | DES-COMM-01 | US-124 / email_prefs.py | TC-063 | Passed |  | Test | Verified | A. Lee
REQ-047 | System shall comply with GDPR data deletion requests within 30 days. | Compliance-8 | High | DES-COMM-02 | US-125 / gdpr_delete.py | TC-064 | In Progress |  | Inspection | In Progress | A. Lee | Legal review pending
REQ-048 | System shall provide users with a downloadable copy of their personal data. | Compliance-9 | High | DES-COMM-03 | US-126 / data_export_gdpr.py | TC-065 | Not Started |  | Test | Not Started | A. Lee
REQ-049 | System shall display cookie consent banner on first visit. | Compliance-10 | Medium | DES-UI-06 | US-306 / cookie_consent.py | TC-066 | Passed |  | Test | Verified | A. Lee
REQ-050 | System shall support dark mode theme toggle. | BRD-3.3 | Low | DES-UI-07 | US-307 / dark_mode.py | TC-067 | Passed |  | Test | Verified | A. Lee
REQ-051 | System shall allow users to customize dashboard widget layout. | BRD-3.4 | Low | DES-UI-08 | US-308 / widget_layout.py | TC-068 | Not Started |  | Test | Not Started | A. Lee
REQ-052 | System shall integrate with third-party calendar services (Google, Outlook). | SRS-5.6 | Medium | DES-API-06 | US-406 / calendar_sync.py | TC-069, TC-070 | In Progress |  | Test | In Progress | J. Smith
REQ-053 | System shall send push notifications for critical account alerts. | SRS-3.9 | Medium | DES-NOTIFY-01 | US-209 / push_notify.py | TC-071 | Not Started |  | Test | Not Started | M. Chen
REQ-054 | System shall support bulk import of records via CSV upload. | SRS-3.10 | Medium | DES-IMPORT-01 | US-210 / bulk_import.py | TC-072, TC-073 | Passed |  | Test | Verified | M. Chen
REQ-055 | System shall validate imported CSV data and report errors row-by-row. | SRS-3.11 | Medium | DES-IMPORT-02 | US-211 / csv_validate.py | TC-074 | Passed |  | Test | Verified | M. Chen

## 2-Legend & Instructions
How to Use This RTM Template
Column Definitions:
Req ID: Unique identifier for each requirement (e.g., REQ-001).
Requirement Description: Clear, testable statement of what the system must do.
Source / Origin: Where the requirement came from (BRD, SRS, stakeholder, regulation).
Priority: Business priority: High / Medium / Low.
Design Doc Ref: Reference to design specification or architecture doc covering this requirement.
Dev / Build Ref: Reference to the user story, ticket, or code module implementing it.
Test Case ID: ID(s) of test case(s) that verify this requirement.
Test Status: Passed / Failed / In Progress / Not Started / Blocked.
Defect ID: Linked defect/bug ID if the test failed.
Verification Method: Test, Inspection, Analysis, or Demonstration.
Status: Overall traceability status: Verified / In Progress / Not Started / At Risk.
Owner: Person accountable for this requirement's verification.
Comments: Notes, risks, or follow-up actions.